GEF-8 CHILD PROJECT CONCEPT

GENERAL CHILD PROJECT INFORMATION

| Child Project Title: | Promoting circular solutions to single-use plastic production and consumption in Lao PDR |  |  |
| --- | --- | --- | --- |
| Country(ies): | Lao PDR | GEF Child Project ID: |  |
|  |  | Type of Child Project | Full-sized Child Project |
| GEF Agency(ies): | WWF-US | GEF Agency Child Project ID: | G0042 |
| Anticipated Executing Entity(s) and Type: | Ministry of Environment and Natural Resources (MONRE) | Government |  |
| GEF Focal Area(s): | International Waters | Submission Date: |  |
| Type of Trust Fund: | GEF Trust Fund | Child Project Duration (Months) | 60 |
| GEF Child Project Grant: (a) | 3,978,440 | GEF Child Project Non-Grant (b) | N/A |
| Agency Fee(s) Grant: (c) | 358,060 | Agency Fee(s) Non-Grant: (d) | N/A |
| Total GEF Financing: (a+b+c+d) | 4,336,500 | Total Co-financing: | 4,010,000 |
| PPG Amount (e): | 150,000 | PPG Agency Fee(s) (f): | 13,500 |
| Total GEF Resources (a+b+c+d+e+f) | 4,500,000 |  |  |
| Project Sector (CCM only) |  |  |  |
| Program | Circular Solutions to Plastic Pollution Integrated Program |  |  |

### CHILD PROJECT FINANCING TABLES

### GEF Financing Table

Indicative Trust Fund Resources Requested by Agency(ies), Country(ies), Focal Area and the Programming of Funds

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing | Agency Fee | Total GEF Financing |
| WWF-US | GEF TF | Lao PDR | International Waters | IW IP Contribution | 3,978,440 | 358,060 | 4,336,500 |
| Total GEF Resources |  |  |  |  | 3,978,440 | 358,060 | 4,336,500 |

### Project Preparation Grant (PPG)

Is Project Preparation Grant requested?       Yes          ☐ No

If yes: fill in PPG table (incl. PPG fee)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | PPG | Agency Fee | Total PPG Funding |
| WWF-US | GEF TF | Lao PDR | International Waters | IW IP Contribution | 150,000 | 13,500 | 163,500 |
| Total PPG Amount |  |  |  |  | 150,000 | 13,500 | 163,500 |

### Sources of Funds for Country STAR Allocation

| GFEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Source of Funds | Total |
| --- | --- | --- | --- | --- | --- |
| N/A | N/A | N/A | N/A | N/A | N/A |
| Total GEF Resources |  |  |  |  |  |

### Indicative Focal Area Elements

| Programming Directions | Trust Fund | (in $) |  |
| --- | --- | --- | --- |
|  |  | GEF Project Financing | Co-financing |
| Plastics IP | GEF TF | 3,978,440 | 4,010,000 |
| Total Project Cost | GEF TF | 3,978,440 | 4,010,000 |

### Indicative Co-financing

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| GEF Agency | WWF-US | In-kind | Recurrent Expenditure | 540,000 |
| CSO | WWF-Laos | In-kind | Recurrent Expenditure | 250,000 |
| Recipient Country Government | MONRE (Govt of Laos) | In-kind | Recurrent Expenditure | 220,000 |
| Donor Agency | Agence Française de Développement (GEF France) | Grant | Investment Mobilized | 3,000,000 |
| Total Co-financing |  |  |  | 4,010,000 |

Agence Française de Développement has indicated interest in providing co-finance to this project. This will be confirmed based on approval of GEF funding.

An additional 4M in co-financing is being discussed between WB and GoL and will be added if confirmed.

TABLE ON CORE INDICATORS

### Core Indicators

| Project Core Indicators |  | Expected at PFD |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management (hectare) | N/A |
| 2 | Marine protected areas created or under improved management (hectare) | N/A |
| 3 | Area of land and ecosystems under restoration (hectare) | N/A |
| 4 | Area of landscapes under improved practices (hectare) | N/A |
| 5 | Area of marine habitat under improved practices (hectare) | N/A |
| 6 | Greenhouse Gas Emissions Mitigated (metric ton of CO2e) | 133,690 mt of CO2e |
| 7 | Shared water ecosystems under new or improved cooperative management (count) | 7.4 = 1 (now) > 3 (with GEF project) |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (metric ton) | N/A |
| 9 | Chemicals of global concern and their waste reduced (metric ton of toxic chemicals reduced) | 39,967 mt |
| 10 | Persistent organic pollutants to air reduced (gram of toxic equivalent gTEQ) | 5 gTEQ |
| 11 | People benefiting from GEF-financed investments disaggregated by sex (count) | 56,200 |

Explain the methodological approach and underlying logic to justify target levels for Core and Sub-Indicators (max. 250 words, approximately 1/2 page)

- The target value of Core Indicators 6, 9 and 10 is calculated based on the methodological approach provided by the GEF IP Circular Solutions to Plastic Pollution, and using the baseline estimation provided by the 2021 World Bank Report ‘Supporting Lao PDR to improve solid and plastic waste management’ which estimates the national rate of waste generation at 910,000 metric tonnes per year, 20% of which are plastic waste.

- The baseline under Core Indicator 7.4 is currently limited (1 = No participation).

- The target value of Core Indicator 11 is composed of the following:

- 100 national-level government officials and 300 city level officials (65% men; 35% women) informed/trained on policy best practices regarding SUP reduction of circularity for plastics; and involved in policy development.

- 500 representatives (60% men; 40% women) of beverage, food and hospitality businesses are consulted on policies and provide input to policy development

- 300 representatives (60% men; 40% women) of food, beverage and hospitality businesses commit to reduce the use of plastic packaging and create and/or distribute environmentally-friendly products through innovative circular business models

- 5,000 workers (60% men; 40% women) of food, beverage and hospitality businesses are engaged in creating and/or distributing environmentally-friendly products through innovative circular business models

- 50,000 consumers (50% men; 50% women) are directly reached out through various campaign initiatives.

PROJECT DESCRIPTION

- Country Context (maximum 500 words)

Describe the country’s relevant environmental challenges and strategic positioning relative to the systems transformation proposed for the program, including relevant existing policies, commitments, and investment frameworks. How are these aligned with the proposed approach to foster impactful outcomes with global environmental benefits?

Environmental challenges

4. A growing economy, increasing tourism and changing urban lifestyle has seen Laos’ urban areas increasingly struggling with plastic pollution. According to a World Bank study, approximately one quarter of waste produced in major cities in Lao PDR is single-use plastics (SUP). In major Lao PDR cities, food and beverage packaging make up half of all plastic pollution, with plastic bottles, lids and caps being the most commonly found items. The hospitality sector contributes heavily towards the demand for plastic food and beverage packaging to be imported and produced, and resultant waste. The importation of secondary raw plastic materials increased four-fold between 2018 and 2019, reaching 18,361 tons of materials imported in 2019.

5. Plastic pollution causes serious public health (e.g. respiratory infection due to open waste burning) and environmental problems, including riverine plastic pollution which not only is a threat to Laos’ aquatic biodiversity and ecosystems but also to the health and welfare of the low-land population in Laos and downstream Mekong countries who relies on the Mekong River resources for their livelihoods. Due to a lack of empirical data, it is estimated that the quantities of plastic waste pollution of the Mekong River in Lao PDR are in the magnitude of 70-1,400 tons of plastic/year. A recent study in the That Luang wetland in Vientiane province showed high levels of microplastic in fish, surface water, and sediment. Riverine plastic pollution also contributes indirectly to marine plastic pollution downstream. While precise data are also lacking on this point, previous surveys estimate the annual plastic input to the ocean from the Mekong River ranging between 18,800-40,000 tonnes per year.

Strategic positioning

6. Addressing plastic pollution is emerging as a Lao government priority, as demonstrated by the focus of the National Green Growth Strategy 2030 (NGGS 2030) which envisions the transition from a linear to circular economy in support of sustainable growth, a low carbon and climate resilient economy, and a safer, healthier, and cleaner environment. Waste management, including that of plastic waste, is a key element of Laos NGGS 2030.  With the support of the World Bank and the European Union, the Ministry of Natural Resources and Environment (MONRE) is currently finalizing the development of the country’s first National Plastics Action Plan (NPAP). The elimination and reduction of SUP is intended to be one key component of the NPAP. MONRE is also creating a National Policy of Hazardous Waste and Plastic Waste Management, while the Ministry of Industry and Commerce administered in 2019 a Ministerial Order on the Suspension of New Business Operation of Industrial Processing Factories Utilising Plastic Waste as Materials, demonstrating a strong commitment to plastic use reduction.

- Project Overview and Approach (maximum 1250 words)

- Provide a brief description of the geographical target(s), including details of systemic challenges, and the specific environmental threats and associated drivers that must be addressed;

7. The project intends to work both at national and sub-national levels, targeting three cities: Vientiane, Vang Vieng, and Luang Prabang. A mapping of plastic pollution hotspots by the World Bank in those three cities shows that especially tourism-related restaurants, bars, cafés and hotels, many of which located along rivers, are hotspots of SUP use and pollution.  All three target cities have stated ambition to become ‘clean and green’ cities.

8. Systemic challenges and drivers of plastic pollution within the three cities and nationally include: (1) a fragmented legislative framework that is mostly focused on downstream interventions; (2) insufficient measures and incentives to drive and support private sector and consumers to reduce production and use of plastic packaging, and investing in circular solutions; (3) increasing imports of plastics, with limited capacity to process this waste; (4) changing consumer habits and lifestyles, especially among a growing urban population,  which has resulted in increased volume of SUP from supermarkets, food takeaways and online purchasing for home deliveries; and (5) increased tourism and greater connectivity  which are associated with an increase in SUP.

- Describe the existing or planned baseline investments, including current institutional framework and processes for stakeholder engagement and gender integration;

Baseline investments:

9. The project baseline consists of public investments from the Government of Laos, as well as initiatives by international organizations and non-governmental organizations. Relevant organizations undertaking and contributing to a strong baseline of work include: World Bank (through their Environmental and Waste Management Project, which supported the development of the NPAP), Agence Française de Développement, the European Union (including development and support for a Sustainable Consumption and Production (SCP) Roadmap), Global Green Growth Institute/KOICA (Green Cities Development Pilot Program), and Plan International (promoting plastic free tourism industry), WWF (Plastic Smart Cities), Swiss Contact and GIZ are contributing to waste management measures. The institutional framework is included in section 1.

Stakeholder engagement

10. An initial list of stakeholders has been identified. This includes government agencies at the national level (MONRE and Department of Environment, Ministry of Industry and Commerce, Ministry of Education, Ministry of Information, Culture, and Tourism), Municipal level (Administration Agencies of Vientiane, Van Vieng and Luang Prabang), business associations, local NGOs (Zero Waste Laos, Plastic Free Lao, Green Vientiane), inter-government organizations (MRC, UNEP), research institutes, and universities.

11. During project development, a detailed stakeholder analysis and plan for engagement will be developed. Stakeholders will be engaged in an appropriate, inclusive, and gender-sensitive manner to inform project design and throughout project execution.

Gender Integration

12. Women face higher dependence on SUP given their prime household management role. In this regard, women have a high capacity for leading on household consumer habits and raising public awareness on environmental threats. The project will engage women as prime consumers through, for example, household-level campaigns to influence women’s consumption choice towards less packaging. Additionally, the project will ensure that female entrepreneurs are well represented in policy consultations and industry-wide dialogues aimed at promoting upstream and midstream solutions to SUP reduction, while empowering female  entrepreneurs as innovators of refill/reuse systems and environmentally-friendly alternative packaging products.

- Describe how the integrated approach proposed for the child project responds to and reflects the Program’s Theory of Change, and as such is an appropriate and suitable option for tackling the systemic challenges, and to achieve the desired transformation with multiple global environmental benefits;

13. The proposed project is in line with the GEF Plastic IP ToC in that it aims at addressing the main source of plastic pollution in the country - i.e. beverage and food packaging - through a combination of upstream and midstream interventions targeting policy-makers at national and subnational levels, relevant private sector industries and consumers. By doing so, the project is expected to contribute to GEBs tied to four GEF focal areas:

- Biodiversity –  reducing impacts of plastic pollution on terrestrial and aquatic ecosystems

- International Waters – reducing impacts to transboundary Mekong River ecosystems and reducing ocean plastic pollution

- Chemicals and Waste – reducing chemicals of global concern and the release of POPs

- Climate Change Mitigation – reducing GHG emissions associated with the plastic lifecycle.

14. Co-benefits also include economic benefits (e.g. reduced waste volumes leading to savings in waste collection and disposal); health benefits (e.g. reduced air pollution); and social benefits (e.g. visual appearance).

- Describe the project’s incremental reasoning for GEF financing under the program, including the results framework and components.

15. Over a five-year period, the project will, in support of Laos NPAP, aim at reducing the production and use of problematic single-use plastic beverage and food packaging and increase the market share of suitable environmentally-friendly alternatives through upstream and midstream approaches targeting policy makers, private sector actors and consumers.

The project will have four components:

Component 1: Enabling regulatory framework

Outcome 1.1: Regulators develop and implement policies that control the import and use of SUP

Activities:

- Build private sector and public capacity for policies development and implementation.

- Identify in consultation with the hospitality, and food & beverage sectors a list of problematic SUP to be phased out, and agree on a roadmap for implementation.

- Develop national guidelines and certification system on reducing and eliminating problematic plastic beverage/food packaging for restaurants, cafes, hotels, boat cruise operators, food delivery companies,  schools and offices

- Create regulations to increase the import tax on SUP

- Support the three target cities with the development of city-level Plastic Action Plans in support of the NPAP

Outcome 1.2: Regulators develop and implement policies that incentivize circularity for plastics

Activities:

- Build private sector and public capacity for policies development and implementation

- Set circularity requirements for SUP product design

- Create a policy on Extended Producer Responsibility, including ecomodulation

- Identify and scale up fiscal policies, blended finance mechanisms and de-risking solutions to support innovative business models and technologies.

Component 2: Private sector engagement

Outcome 2.1: Food, beverage and hospitality industry actors commit to reduce the use of SUP and create and/or distribute environmentally-friendly products through innovative circular business models

Activities:

- Create engagement mechanisms to ensure stakeholder groups are consulted on policy and business model solutions.

- In support of national guidelines to reduce/eliminate  problematic and unnecessary plastic beverage/food packaging, facilitate industry-specific business ambition on SUP reduction and circular alternatives through dialogue with the food, beverage and hospitality sectors

- Support local governments to implement plastic-smart certification of hotels/cafes/restaurants/food delivery companies/boat cruise operators complying with national guidelines.

Outcome 2.2: Food, beverage and hospitality industry actors engage in pilot business models to increase the uptake of environmentally-friendly products, reducing the use of SUPs

Activities:

- Launch an innovation competition  to support social enterprises to develop reusable  food and beverage packaging systems and test them in collaboration with pilot food delivery companies and/or restaurants

- Testing out a deposit return scheme system which tie up to several major convenient stores to enable customers to return plastic products

- Launch an innovation competition to support social enterprises to innovate on bio-based packaging and test out products with pilot restaurants, hotels, markets and food delivery companies and/or with food producers.

Component 3:   Behavior and social changes

Outcome 3.1: Citizens in the three target cities increase participation in use of circular / sustainable offerings for food and beverage, and demonstrate support for policy creation, accelerating the implementation of components 1 and 2

Activities:

- Support the roll-out of plastic-free day to accelerate implementation of components 1 and 2

- Support pilot schools and offices to apply national guidelines to become ‘Plastic-Smart Schools’ and  ‘Plastic-Smart Offices’

- Ban the use of plastic bags in pilot supermarkets and wet markets and encourage people to bring their own reusable bag.

- Conduct online/offline household-level campaigns to educate consumers choice toward less packaging

- Collaborate with tour operator/hotel/restaurant associations to promote plastic-smart restaurants/cafes/hotels/boat cruise operators among tourists.

Component 4: Knowledge Management, Communication, and Program-level Coordination

Outcome 4.1: Assessment and knowledge sharing support awareness-raising, upscaling, and more transparent coherent decision making.

Activities:

- Facilitate the participation of national and sub-national level government representatives and private sector representatives to relevant national/regional/international networks/forums for knowledge/best practices sharing

- In partnership with MRC, UNEP, research institutes and local universities, produce knowledge products on project’s achievements, best practices and lessons learned

- Organize events to disseminate knowledge products

Outcome 4.2. Project intervention and achievements align with the Global Coordination Project

Activities:

- Ensure strong engagement with the Global Coordination Project of the Circular Solutions to Plastic Pollution IP to share and replicate results. This includes participation in IP conferences and webinars, knowledge exchanges, and coordination/collaboration with other child projects (particularly Cambodia on any regional efforts).

- Engagement with the Global / Regional Framework (maximum 500 words)

Describe how the project will align with the global / regional framework for the program to foster knowledge sharing, learning, and synthesis of experiences. How will the proposed approach scale-up from the local and national level to maximize engagement by all relevant stakeholders and/or actors?

16. Project component 4, dedicated to knowledge management, communication and coordination, will be linked to the Global Coordination Project of the Circular Solutions to Plastic Pollution Integrated Program. The project is committed to sharing knowledge and participating in events hosted by the Plastics Global Coordination Project (annual conferences, webinars, exchanges, knowledge products) to exchange on best practices, experiences and lessons learned that can be replicated in Laos and vice-versa. Accordingly, results from the project will be disseminated within and beyond the project intervention area through the Plastic IP Global Coordination Project and any existing information sharing networks (e.g. WWF-supported Plastic Smart Cities, WWF-supported PACT, etc.) and forums (MRC, ASEAN, UNEP, GEF IP Annual Workshops, etc.). The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to the project. The project will identify, analyze and share lessons learned that might be beneficial to the design and implementation of similar projects and disseminate these lessons widely. There will be continuous information exchange between this project and other projects of similar focus in the same region and globally. The project budget will include funding for key staff to attend the IP Annual Workshops, and all project management unit staff will have part of their time dedicated to coordinating with the Global Project and the Global PMU. For example, the Laos project communications officer will coordinate with the Global Project communications staff, the Laos project M&E officer will work with the Global Project M&E staff.

ANNEX - TABLE B

| Project Objective: | To reduce the production and use of problematic single-use plastic beverage and food packaging and increase the market share of suitable environmentally-friendly alternatives through an integrated upstream approach targeting policy makers, private sector actors and consumers |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Program Components | Component Type | Program Outcomes | Trust Fund | (in $) |  |
|  |  |  |  | GEF Program Financing | Co - financing |
| Component 1: Enabling regulatory and policy framework | TA | Outcome 1.1.: Regulators develop and implement policies that control the import and use of single use plastic Outcome 1.2.: Regulators develop and implement policies that create and incentivize circularity for plastics. | GEF TF | 757,798 | 763,809 |
| Component 2: Private sector engagement | INV | Outcome 2.1.: Food, beverage and hospitality industry actors commit to reduce the use of plastic packaging and create and/or distribute environmentally-friendly products through innovative circular business models, reducing the use of SUPs Outcome 2.2.: Food, beverage and hospitality industry actors engage in pilot business models to increase the uptake of environmentally-friendly products through innovative circular business models, reducing the use of SUPs | GEF TF | 1,326,146 | 1,336,666 |
| Component 3: Behavior and social changes | TA | Outcome 3.1: Citizens increase participation in and use of circular / sustainable offerings for food and beverage, and demonstrate support for policy creation, accelerating the implementation of components 1 and 2 | GEF TF | 947,247 | 954,761 |
| Component 4: Knowledge Management, Communication, and Program-level Coordination | TA | 5.1. Knowledge sharing and learning activities developed to support awareness-raising, upscaling, and more transparent coherent decision making. 5.2. Coordination with the global program | GEF TF | 568,348 | 572,857 |
| M&E | TA | Effective on-going Monitoring and Evaluation. | GEF TF | 189,450 | 190,953 |
| Subtotal |  |  |  | 3,788,991 | 3,819,046 |
| Program Management Cost (PMC) |  |  |  | 189,450 | 190,954 |
| Total Program Cost |  |  |  | 3,978,440 | 4,010,000 |

World Bank, Supporting Lao PDR to improve solid and plastic waste management: solid waste assessments’ (2021a), p.17.

Based on current average gender distribution among government civil servants.

World Bank. Supporting Lao PDR in Development of a Plastic Action Plan : Plastic Diagnostics (2021b).

World Bank (2021b).

World Bank (2021b), p.45.

World Bank, Get CLEAN and GREEN—Solid and Plastic Waste Management in Lao PDR, 2022, p.14.

World Bank (2021b), p.45. UNEP’s CounterMEASURE project aims to fill the data gap on plastic river pollution and interaction with biodiversity.

Expected to be endorsed by June 2023.

Mekong River Commission, (2022).

No. 0930/MoIC.DIH, 2019